## Template
|  | PMO Email: | PMO@uconn.onmicrosoft.com
|  | Website: | https://pmo.its.uconn.edu/
ITS PMO - Project Communication Plan
Project Name:
Project Manager:
Executive Sponsor:
Principal Stakeholder:
Date:
Deliberable Info (What) | Recipients (Who) | Delivery Methods (How) | Schedule (When) | Who's Responsible? (Owner)
Project Information | Project Team | SharePoint Team Meetings Email | As Needed | Project Manager
Project Status | Project Stakeholders PMO Manager | Email (Status Report) SharePoint | By 12:00pm (noon) every Monday | Project Manager
Agenda/Minutes | Project Team | Email SharePoint Team Meetings | 24hrs after each meeting/As Needed | Project Manager
Timeline Update | Project Team Project Stakeholders Executive Sponsors PMO Manager | Meetings Email SharePoint | As Needed | Project Manager
Project Updates Action Item Status | Project Manager | Team Meetings Email Conference Calls | As Needed | Project Team
Project Risks | Project Team PMO Manager Project Stakeholders Executive Sponsors | Risk Matrix Meeting Minutes | AS Needed | Project Manager

## Sample
ITS PMO - Project Communication Plan
Project Name: | Peoplesoft CS (Student) 9.2 Upgrade
Project Manager: | Ben Daniels
Executive Sponsor: | Michael Mundrane
Principal Stakeholder: | Nathan Fuerst
Date: | 2020-06-16
Deliberable Info (What) | Recipients (Who) | Delivery Methods (How) | Schedule (When) | Who's Responsible? (Owner)
Project Information | Project Team | SharePoint Team Meetings Email | Monday Stand-Up, Thursday Full Team Meeting | Project Manager
Project Status | Project Stakeholders PMO Manager | Weekly Status Report Email SharePoint | By 11:00am every Wednesday | Project Manager
Agenda/Minutes | Project Team | Email SharePoint Team Meetings | After each meeting/As Needed | Project Manager / Project Leads
Timeline Update | Project Team Project Stakeholders Executive Sponsors PMO Manager | Meetings Email SharePoint | COB on Fridays | Project Manager
Project Updates Action Item Status | Project Manager Project Leads | Team Meetings Email Conference Calls | As Needed | Project Team
Project Risks | Project Team PMO Manager Project Stakeholders Executive Sponsors | Status Reports Risk Section Meeting Minutes | Weekly Updates/As Needed | Project Manager