## lessons Learned
ITS PMO - Lessons Learned
| PMO Email: | PMO@uconn.onmicrosoft.com
| Website: | https://pmo.its.uconn.edu/
The purpose of this report is to capture insights gained on a project. This report should be used and filled out throughout the project. Feedback from all stakeholder groups should be solicited at the end of the project for inclusion in the Lessons Learned.
Project Name:
Project Manager:
Date:
Were the Goals Achieved?
Yes
No
What Went Well?
1
2
3
4
5
6
7
8
9
10
11
12
What Could We Have Improved Upon?
1
2
3
4
5
6
7
8
9
10
11
12
What Changes Could We Make to Our Processes Moving Forward Based on These Findings?
1
2
3
4
5
6
7
8
9
10
11
12

## Sample
ITS PMO - Lessons Learned
| PMO Email: |  | PMO@uconn.onmicrosoft.com
| Website: |  | https://pmo.its.uconn.edu/
The purpose of this report is to capture insights gained on a project. This report should be used and filled out throughout the project. Feedback from all stakeholder groups should be solicited at the end of the project for inclusion in the Lessons Learned.
Project Name: |  | Groton Network Upgrade
Project Manager: |  | Catherine Rhodes & John Letot
Date: |  | 2023-09-27
Were the Goals Achieved?
Yes | Upgrade the Groton network to support DR services.
Yes | Implement BGP so Groton can run independently in case of a disaster.
Yes | Remove all old equipment. Scope of the project was adjusted to remove the requirement to migrate Exadata. This requirement was moved to another project, per Director.
Yes | Replace end-of-life firewall.
Yes | Add an internet border firewall.
Yes | Replace the vendor VPN.
What Went Well?
1 | The network configuration buildout was good but the team had to create hundreds of new firewall rules.
2 | Made it through COVID.
3 | Had good participation in the regularly scheduled status meetings in Teams.
4 | Allocation of resources was good after the PMO was involved - about halfway through.
5 | The scheduling of installs ahead of time.
6 | This was a major upgrade that was completed successfully with very little fallout, in spite of COVID occurring right in the middle of it.
What Could We Have Improved Upon?
1 | Security was caught off guard by the hundreds of changes to the firewall rules.
2 | Took too long to get equipment - hampered by COVID.
3 | Took too long to do the work due to traveling back and forth with equipment.
4 | Due to the delays incurred by COVID, components changed, which caused a snowball effect leading to design changes and scope creep.
5 | Some meetings had too many people.
6 | Some meetings needed more people.
What Changes Could We Make to Our Processes Moving Forward Based on These Findings?
1 | We have an issue with identifying new firewall rules needed when upgrading firewalls. - Could have more detailed meetings to brainstorm about possible new firewall rules needed during firewall upgrades.
2 | Have the PMO involved earlier in the project.
3 | When upgrading equipment at remote locations, and where possible, stage and test the equipment locally before installing the new equipment remotely.
4 | Send at least two people to the remote site when doing physical work to reduce time spent.
5 | For more specialized meetings, other than general status meetings, limit the attendance to only the ones necessary. Then summarize the results in the next general status meeting.
6 | Recognize the need to allocate resources to projects sooner in the project lifecycle.