## Slide 1
Summary: Weekly project status report will be updated and sent when requests are made.
Definition of Done:
Project Activity | 
Accomplishments: | Next Steps:
Add accomplishment | Follow-up with…
Action Items |  |  |  |  |  |  | 
ID | Owner | Action Item | Estimate | Actual | Date Opened | Due Date | Notes
1 |  |  |  |  |  |  | 
Project Schedule |  |  | 
# | Milestone | Target | Revised
1 | End of 6-month Support Period | July 31 | 
Project Key Risks/Issues |  |  | 
# | Risk/Issue | Impact | Mitigation/Resolution
1 |  |  | 
Project Name:
Name
Date:
2/12/2024
Scope
Schedule
Budget
Critical Success Factors

## Slide 2
Action Items cont. |  |  |  |  |  |  | 
ID | Owner | Action Item | Estimate | Actual | Date Opened | Due Date | Notes
Project Help | 
PMO Email: | PMO@uconn.onmicrosoft.com
PMO Website: | https://pmo.its.uconn.edu/
Notes: RAID Slide – use to determine Business Outcomes – If implications are becoming realized, this needs to downgrade in status. This report is our weekly analysis of how we are moving the project along to meet our commitments in our contracts with our customers. We need to look around corners and understand what is coming, not just what has happened.
Do not use the word ‘Hope’ in business strategy conversations – we are planning, have a mitigation strategy, etc.
Add in information on how to complete this so we have consistency - process to gather and complete. Set expectations.
Low Risk, Med risk, High risk,
Color coding > where there needs attention

## Slide 3
Summary: Project is behind schedule and will not achieve Go Live of January, 2024. Team determining new Go Live date. Currently in Implementation phase, testing and remediating discovered issues. Vendor developing required customizations.
Definition of Done: UConn University Safety utilizing VCS as time & labor system of record, and legacy PSP application fully retired.
Project Activity | 
Accomplishments: | Next Steps:
Completed initial supervisor time pilot Remediated multiple issues discovered in initial pilot group testing. Completed additional development work on Shift Differential and Overtime Sorting customizations. Completed some additional work on CoreCT time balance upload file. | Determine alternate Go Live date. Complete SSO configuration. Complete shift differential customization development for FD and PD. Complete initial version of CoreCT time balance upload file and send to VCS for review Validate holiday pay rules and data, and send to VCS for review.
Action Items |  |  |  |  |  |  | 
ID | Owner | Action Item | Estimate | Actual | Date Opened | Due Date | Notes
1 | VCS | PD Extended Rotation enhancement |  |  | 7/21/2023 | TBD | VCS to get clarification on this item
2 | VCS | OT Hiring |  |  | 8/1/2023 | 2/23/2024 | VCS developing
3 | VCS | Shift Differential for payroll export |  |  | 9/30/2023 | 2/23/2024 | VCS developing
Project Schedule |  |  | 
# | Milestone | Target | Revised
1 | SSO configured | 7/7 | 1/31
2 | Begin Supervisor Pilot | 12/6 | Complete
3 | Complete Payroll Export | TBD | 
Project Key Risks/Issues |  |  | 
# | Risk/Issue | Impact | Mitigation/Resolution
1 | Resource contention | Moderate | Vendor increasing assigned staff on project.
2 | Custom development | Low | Development activities may impact timeline. Determine process workarounds where practical.
Project Name:
VCS Implementation
Date:
1/29/2024
Scope
Schedule
Budget
Critical Success Factors