## Blank RACI
|  | PMO Email: | PMO@uconn.onmicrosoft.com
|  | Website: | https://pmo.its.uconn.edu/
RACI Chart (Roles and Responsibilities Matrix)
| Process Name / Description: | Describe the project or process that this RACI addresses
| Created On: | Date | Revision: | Date last revised
| Created by: | Note all team members/functions who developed and agreed to this RACI
# | Task | Function A | Function B | Function C | Function D | Function E
1 | First Responsibility
2 | Second…
3 | Third…
4 | Fourth…
5 | Fifth…
6 | Sixth…
7
8
R = Responsible, A = Accountable, C = Consulted, I = Informed

## Example 1
|  | PMO Email: | PMO@uconn.onmicrosoft.com
|  | Website: | https://pmo.its.uconn.edu/
RACI Chart (Roles and Responsibilities Matrix)
| Process Name / Description: | Migrate identified services off of legacy departmental firewall and onto new infrastructure.
| Created On: | 2022-04-01 | Revision: | 2023-03-12
| Created by: | Ben Daniels (ITS PMO)
# | Task | PMO | Security | ITS ES | ITS NetEng | Departments | Leadership (Chris, MM)
1 | Install and configure hardware | I | A | C | R | I
2 | Design firewall rules - Document firewall policy sets for departmental services keeping in mind security best-practices and future-state strategies. | I | A/R | I | C | R
3 | Implement firewall rule changes - Implement firewall rulesets in new hardware based on documentation keeping in mind security best-practices and future-state strategies. | I | A/R | I | C | C
4 | Perform audit of existing departmental firewall to gather full inventory | I | A/R | I | C | R
5 | Create a list of departments | I | A/R | I | I | C
6 | Send general communication regarding firewall being end-of-life for non-ITS departments | C | A/R | I | I | I
7 | Validate list of departmental contacts (service owners) | I | A/R | I | I | C
8 | Determine which departments are like-for-like | I | A/R | I | C | C
9 | Determine the work to provision interfaces and VLANs | I | A/R | C | R | I
10 | Communicate new firewall policies | C | A/R | I | I | I
11 | DUPE | I | A/R | I | I | C
12 | Publish new firewall policies | I | A/R | I | I | I
13 | Provision VLANs and interfaces in network architecture | I | A/R | I | R | I
14 | Provision firewall nterfaces | I | A/R | I | I | I
15 | Provide VPLS network design | I | C | I | A/R | N/A
16 | Determine migration approach for individual departments | I | A/R | I | I | C
17 | Determine migration timings for individual departments | I | A/R | I | I | C
18 | Finalize and Publish migration dates | A/R | C | C | C | C
19 | DUPE | A/R | C | C | C | C
20 | Build migration schedules | A/R | C | C | C | C
21 | Monitor and report on project status | A/R | C | I | C | I C
22 | Deliver project successfully within scope, schedule, and budget | R | C | R | R | R | C
R = Responsible, A = Accountable, C = Consulted, I = Informed

## Example 2
|  | PMO Email: | PMO@uconn.onmicrosoft.com
|  | Website: | https://pmo.its.uconn.edu/
RACI Chart (Roles and Responsibilities Matrix)
| Process Name / Description: | Kuali migration to the Cloud (Planning Phase)
| Created On: | 09.09.2022 | Revision: | 03.30.2023
| Created by: | John Letot, UConn PMO
# | Task | PMO | Enterprise Apps | Vendor | Leadership | Stakeholders
1 | Communication for the project | R | A | R | I | I
2 | Coordinate with service owners to verify customizations | I | R/A | R | A | C
3 | Updating team on customization review progress | C | R/A | R | I | I
4 | Provide training for the overall system | I | A | R | I | I
5 | Creating Project Plan/Schedule for Planning Phase | R | A | R | I | I
6 | Define scope for overall implementation | R | A | R | I | I
R = Responsible, A = Accountable, C = Consulted, I = Informed